## HOME
AL-SHIFA POLYCLINIC
Version Number : Verified By :Rugma Raghav Environment Details :Windows 11, Google Chrome(120) |  |  |  | Tested By :Amal Jose Date :01-04-2024 Module Name :Home Page
Test ID | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Status
ALP_HOM_01 | Ensure the home page load with in seconds | 1.Open www.alshifapolyclinic.com 2.Click on the home |  | The page should load with in seconds | The page load with in seconds | Pass
ALP_HOM_02 | Verify the home page is secure | 1.Open www.alshifapolyclinic.com 2.Click on the home |  | Home page should be secure | Home page is secure | Pass
ALP_HOM_03 | Check whether the logo is clearly visible | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Check logo at left top corner |  | Logo should be clearly visible | Logo is clearly visible | Pass
ALP_HOM_04 | Check whether the right arrow on the top of the home page is clickable and move to next page | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Click on the right arrow |  | The right arrow should be clickable and should be able to move to next page | The right arrow is clickable and move to next page | Pass
ALP_HOM_05 | Check whether the left arrow on the top of the home page is clickable and move to next page | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Click on the left arrow |  | The left arrow should be clickable and should be able to move to next page | The left arrow is clickable and move to next page | Pass
ALP_HOM_06 | Verify the homeopathy link is clickable and redirect to the next page | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Click on the homeopathy link |  | Homeopathy link should be clickable and should be able to move to next page | Homeopathy link is clickable and move to next page | Pass
ALP_HOM_07 | Verify the dentistry link is clickable and redirect to the next page | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Click on the dentistry link |  | Dentistry link should be clickable and should be able to move to next page | Dentistry link is clickable and move to next page | Pass
ALP_HOM_08 | Check whether the font size of the text's in the home page are in same size | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Check the font size of the text's in the home page |  | The font size of text's should be same size | The font size of text's are in same size | Pass
ALP_HOM_09 | Verify the alignment of text's under 'Services' title is correct | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Check the alignment of text's under 'Services' title |  | Alignment should be correct | Alignment is not correct | Fail
ALP_HOM_10 | Check whether any spelling mistakes under 'DENTAL IMPLANTS' title | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Check the spelling mistakes under 'DENTAL IMPLANTS' title |  | Spelling of the text's should be correct | Spelling of the text is not correct | Fail
ALP_HOM_11 | Verify all the links under the title 'Services' are clickable and redirect to the next pages | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Click all the links |  | All links should be clickable and redirect to the next pages | All links are clickable and redirects to the next pages | Pass
ALP_HOM_12 | Verify the alignment of text's under 'VISION' title is correct | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Check the alignment of text's under 'VISION' title |  | Alignment should be correct | Alignment is not correct | Fail
ALP_HOM_13 | Verify the alignment of text's under 'MISSION' title is correct | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Check the alignment of text's under 'MISSION' title |  | Alignment should be correct | Alignment is not correct | Fail
ALP_HOM_14 | Check whether any spelling mistakes in the names of doctors | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Check the spelling mistakes in the names of doctors |  | Spelling of the names should be correct | Spelling of the name is not correct | Fail
ALP_HOM_15 | Check whether the right arrow on the bottom of the home page is clickable and move to next | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Click on the right arrow |  | The right arrow should be clickable and should be able to move to next | The right arrow is clickable and move to next | Pass
ALP_HOM_16 | Check whether the left arrow on the bottom of the home page is clickable and move to next | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Click on the left arrow |  | The left arrow should be clickable and should be able to move to next | The left arrow is clickable and move to next | Pass
ALP_HOM_17 | Verify the names and descriptions on the bottom of the home page | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Check the names and descriptions |  | The names should be correct and descriptions should be understandable | Correct names is not there and descriptions is not understandable | Fail
ALP_HOM_18 | Ensure that the social media icons of facebook and instagram on the top of the page is clickable and redirect to respective pages | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Click on the facebook and instagram icons |  | Social media icons should be clickable and should be redirect to respective pages | Social media icons is clickable and redirects to respective pages | pass
ALP_HOM_19 | Verify that the google icon on the top of the page is clickable and redirect to next page | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Click on the google icon |  | Google icon should be clickable and should be redirect to next page | Google icon is clickable and redirects to next page | Pass
ALP_HOM_20 | Verify that the Whatsapp icon is clickable and redirect to next page | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Click on the whatsapp icon |  | Whatsapp icon should be clickable and should be redirect to next page | Whatsapp icon is clickable and redirects to next page | Pass

## ABOUT
AL-SHIFA POLYCLINIC
Version Number : Verified By :Rugma Raghav Environment Details :Windows 11, Google Chrome(120) |  |  |  | Tested By :Amal Jose Date :01-04-2024 Module Name :About
Test ID | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Status
ALP_ABO_01 | Verify the time is taken to load the page | 1.Open www.alshifapolyclinic.com 2.Click on the about |  | The page should be load with in seconds | The page is load with in seconds | Pass
ALP_ABO_02 | Verify the font size of all text's in the about page is correct | 1.Open www.alshifapolyclinic.com 2.Click on the about 3.Check the font size of the text's in the about page |  | Font size of the text's should be correct | Font size of the text's is correct | Pass
ALP_ABO_03 | Ensure the alignment of the text's under 'AL-SHIFA POLY CLINIC' title is correct | 1.Open www.alshifapolyclinic.com 2.Click on the about 3.Check the alignment of the text's under 'AL-SHIFA POLY CLINIC' title |  | Alignment should be correct | Alignment is not correct | Fail
ALP_ABO_04 | Check whether any spelling mistakes in the names of doctors | 1.Open www.alshifapolyclinic.com 2.Click on the about 3.Check the spelling mistakes in the names of doctors |  | Spelling of the names should be correct | Spelling of the name is not correct | Fail
ALP_ABO_05 | Check the alignment of descriptions under the doctors names is correct | 1.Open www.alshifapolyclinic.com 2.Click on the about 3.Check the alignment of descriptions |  | Alignment should be correct | Alignment is not correct | Fail
ALP_ABO_06 | Verify the linkedin and whatsapp icons under the doctors names is clickable and redirect to next page | 1.Open www.alshifapolyclinic.com 2.Click on the about 3.Click on the linkedin and whatsapp icons |  | Icons should be clickable and redirect to next pages | Icons are not clickable | Fail
ALP_ABO_07 | Verify the alignment of text's under 'VISION' title is correct | 1.Open www.alshifapolyclinic.com 2.Click on the about 3.Check the alignment of text's under 'VISION' title |  | Alignment should be correct | Alignment is not correct | Fail
ALP_ABO_08 | Verify the alignment of text's under 'MISSION' title is correct | 1.Open www.alshifapolyclinic.com 2.Click on the about 3.Check the alignment of text's under 'MISSION' title |  | Alignment should be correct | Alignment is not correct | Fail
ALP_ABO_09 | Ensure that the google map is clear and not overlap | 1.Open www.alshifapolyclinic.com 2.Click on the about 3.Check the google map |  | Google map should be clear and should not be overlap | Google map is clear and not overlapped | Pass
ALP_ABO_10 | Ensure that the google map can zoom in and zoom out | 1.Open www.alshifapolyclinic.com 2.Click on the about 3.Click on the zoom in and zoom out button |  | Google map should be able to zoom in and zoom out | Google map is able to zoom in and zoom out | Pass
ALP_ABO_11 | Verify that the Whatsapp icon is clickable and redirect to next page | 1.Open www.alshifapolyclinic.com 2.Click on the about 3.Click on the whatsapp icon |  | Whatsapp icon should be clickable and should be redirect to next page | Whatsapp icon is clickable and redirects to next page | Pass

## HOMEOPATHY
AL-SHIFA POLYCLINIC
Version Number : Verified By :Rugma Raghav Environment Details :Windows 11, Google Chrome(120) |  |  |  | Tested By :Amal Jose Date :01-04-2024 Module Name :Homeopathy
Test ID | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Status
ALP_HMP_01 | Verify the time is taken to load the page | 1.Open www.alshifapolyclinic.com 2.Click on the homeopathy |  | The page should be load with in seconds | The page is load with in seconds | Pass
ALP_HMP_02 | Verify the font size of all text's in the page is correct | 1.Open www.alshifapolyclinic.com 2.Click on the homeopathy 3.Check the font size of the text's in the page |  | Font size of the text's should be correct | Font size of the text's is correct | Pass
ALP_HMP_03 | Check whether the right arrow on the top of the page is clickable and move to next page | 1.Open www.alshifapolyclinic.com 2.Click on the homeopathy 3.Click on the right arrow |  | The right arrow should be clickable and should be able to move to next page | The right arrow is clickable and move to next page | Pass
ALP_HMP_04 | Check whether the left arrow on the top of the page is clickable and move to next page | 1.Open www.alshifapolyclinic.com 2.Click on the homeopathy 3.Click on the left arrow |  | The left arrow should be clickable and should be able to move to next page | The left arrow is clickable and move to next page | Pass
ALP_HMP_05 | Check the alignment of the text's in the page | 1.Open www.alshifapolyclinic.com 2.Click on the homeopathy 3.Check the alignment of the text's in the page |  | Alignment should be correct | Alignment is not correct | Fail
ALP_HMP_06 | Check whether any spelling mistakes in the descriptions | 1.Open www.alshifapolyclinic.com 2.Click on the homeopathy 3.Check the spelling mistakes in the descriptions |  | There should not be any spelling mistakes in the descriptions | Spelling mistakes is not in the descriptions | Pass
ALP_HMP_07 | Verify that the Whatsapp icon is clickable and redirect to next page | 1.Open www.alshifapolyclinic.com 2.Click on the homeopathy 3.Click on the whatsapp icon |  | Whatsapp icon should be clickable and should be redirect to next page | Whatsapp icon is clickable and redirects to next page | Pass

## DENTISTRY
AL-SHIFA POLYCLINIC
Version Number : Verified By :Rugma Raghav Environment Details :Windows 11, Google Chrome(120) |  |  |  | Tested By :Amal Jose Date :01-04-2024 Module Name :Dentistry
Test ID | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Status
ALP_DEN_01 | Ensure the page load with in seconds | 1.Open www.alshifapolyclinic.com 2.Click on the dentistry |  | The page should be load with in seconds | The page is load with in seconds | Pass
ALP_DEN_02 | Verify the font size of all text's in the page is correct | 1.Open www.alshifapolyclinic.com 2.Click on the dentistry 3.Check the font size of the text's in the page |  | Font size of the text's should be correct | Font size of the text's is correct | Pass
ALP_DEN_03 | Check the alignment of the text's in the page | 1.Open www.alshifapolyclinic.com 2.Click on the dentistry 3.Check the alignment of the text's in the page |  | Alignment should be correct | Alignment is correct | Pass
ALP_DEN_04 | Check whether any spelling mistakes in the descriptions | 1.Open www.alshifapolyclinic.com 2.Click on the dentistry 3.Check the spelling mistakes in the descriptions |  | There should not be any spelling mistakes in the descriptions | Spelling mistake is there in the descriptions | Fail
ALP_DEN_05 | Verify that the Whatsapp icon is clickable and redirect to next page | 1.Open www.alshifapolyclinic.com 2.Click on the dentistry 3.Click on the whatsapp icon |  | Whatsapp icon should be clickable and should be redirect to next page | Whatsapp icon is clickable and redirects to next page | Pass

## CONTACT
AL-SHIFA POLYCLINIC
Version Number : Verified By :Rugma Raghav Environment Details :Windows 11, Google Chrome(120) |  |  |  | Tested By :Amal Jose Date :01-04-2024 Module Name :Dentistry
Test ID | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Status
ALP_CON_01 | Verify the time is taken to load the page | 1.Open www.alshifapolyclinic.com 2.Click on the contact |  | The page should be load with in seconds | The page is load with in seconds | Pass
ALP_CON_02 | Check whether the alignment of the text's in the page is correct | 1.Open www.alshifapolyclinic.com 2.Click on the contact 3.Check the alignment of the text's in the page |  | Alignment should be correct | Alignment is not correct | Fail
ALP_CON_03 | Verify that user can see all titles in the page after few seconds of loading | 1.Open www.alshifapolyclinic.com 2.Click on the contact 3.Check the titles of the page after few seconds of loading |  | All titles of the page should be able to see after few seconds of loading | User cannot see'Working Hours' title after loading few seconds | Fail
ALP_CON_04 | Ensure that the google map is clear and not overlap | 1.Open www.alshifapolyclinic.com 2.Click on the contact 3.Check the google map |  | Google map should be clear and should not be overlap | Google map is clear and not overlapped | Pass
ALP_CON_05 | Ensure that the google map can zoom in and zoom out | 1.Open www.alshifapolyclinic.com 2.Click on the contact 3.Click on the zoom in and zoom out button |  | Google map should be able to zoom in and zoom out | Google map is able to zoom in and zoom out | Pass
ALP_CON_06 | Check whether the phone number icon and link is clickable and redirect to next page | 1.Open www.alshifapolyclinic.com 2.Click on the contact 3.Click on the phone number icon and link |  | Phone number icon and link should be clickable and should be redirect to next page | Phone number icon and link is clickable but cannot redirects to next page | Fail
ALP_CON_07 | Check whether the email icon and link is clickable and redirect to next page | 1.Open www.alshifapolyclinic.com 2.Click on the contact 3.Click on the email icon and link |  | Email icon and link should be clickable and should be redirect to next page | Email icon and link is not clickable and cannot redirects to next page | Fail
ALP_CON_08 | Verify that the Whatsapp icon is clickable and redirect to next page | 1.Open www.alshifapolyclinic.com 2.Click on the contact 3.Click on the whatsapp icon |  | Whatsapp icon should be clickable and should be redirect to next page | Whatsapp icon is clickable and redirects to next page | Pass

## BOOK APPOINTMENT
AL-SHIFA POLYCLINIC
Version Number : Verified By :Rugma Raghav Environment Details :Windows 11, Google Chrome(120) |  |  |  | Tested By :Amal Jose Date :01-04-2024 Module Name :Book Appoinment
Test ID | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Status
ALP_BOA_01 | Ensure the page load with in seconds | 1.Open www.alshifapolyclinic.com 2.Click on the book appointment |  | The page should be load with in seconds | The page is load with in seconds | Pass
ALP_BOA_02 | Check whether the logo is clearly visible | 1.Open www.alshifapolyclinic.com 2.Click on the book appointment 3.Check logo at left top corner |  | Logo should be clearly visible | Logo is not clearly visible | Fail
ALP_BOA_03 | Check whether all fields and field names are properly align | 1.Open www.alshifapolyclinic.com 2.Click on the book appointment 3.Verify the fields and field names |  | All fields and field names should be properly aligned | All fields and field names are properly aligned | Pass
ALP_BOA_04 | Check whether all mandatory fields have asterick symbol (*) | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Verify the fields |  | Should contain asterick symbol | Asterick symbol is not present | Fail
ALP_BOA_05 | Verify that the send button is clickable | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Click on the send button |  | Send button should be clickable | Send button is clickable | Pass
ALP_BOA_06 | Verify that the dropdown field is clickable | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Click on the dropdown field |  | Dropdown field should be clickable | Dropdown field is clickable | Pass
ALP_BOA_07 | Check whether all fields are writable | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Click on each field |  | All fields should be writable | All fields are writable | Pass
ALP_BOA_08 | Verifay that the proper error message will display without entering any data in the fields | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Click on the send button without entering any data |  | Proper error message should be display | Error validation is displayed successfully | Pass
ALP_BOA_09 | Check whether the name field does not accept empty string | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Click on the send button without entering any data on the name field |  | Proper error message should be display | Error validation is displayed successfully | Pass
ALP_BOA_10 | Check whether the name field accept characters | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Enter characters on the field 4.Navigate to next field | Amal | Name field should accept characters | Name field accepts characters | Pass
ALP_BOA_11 | Check whether the name field does not accept numbers and special characters | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Enter special characters and numbers on the field 4.Navigate to next field | 253@$ | Name field should not accept special characters and numbers | Name field accepts special characters and numbers | Fail
ALP_BOA_12 | Verify that the name field does not accept full name without space | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Enter the full name without space 4.Navigate to next field | AmalJose | Name field should not accept full name without space | Name field accepts full name without space | Fail
ALP_BOA_13 | Check whether the contact number field does not accept empty string | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Click on the send button without entering any data on the contact number field |  | Proper error message should be display | Error validation is displayed successfully | Pass
ALP_BOA_14 | Check whether the contact number field accept numbers | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Enter numbers on the field 4.Navigate to next field | 9048965083 | Contact number field should accept numbers | Contact number field accepts numbers | Pass
ALP_BOA_15 | Check whether the contact number field does not accept characters and special characters | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Enter special characters and characters on the field 4.Navigate to next field | gdf@#$ | Contact number field should not accept special characters and characters | Contact number field accepts special characters and characters | Fail
ALP_BOA_16 | Check whether the email field does not accept empty string | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Click on the send button without entering any data on the email field |  | Proper error message should be display | Error validation is displayed successfully | Pass
ALP_BOA_17 | Check whether the email field accept characters, numbers and special characters | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Enter special characters, numbers and characters on the field 4.Navigate to next field | amaljose@996gmail.com | Email field should accept special characters, numbers and characters | Email field accepts special characters, numbers and characters | Pass
ALP_BOA_18 | Verify that the date field does not accept empty string | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Click on the send button without entering any data on the date field |  | Proper error message should be display | Error validation is displayed successfully | Pass
ALP_BOA_19 | Verify that the date field accept valid data | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Enter valid data 4.Navigate to next field | 2024-03-31 | Date field should accept valid data | Date field accepts valid data | Pass
ALP_BOA_20 | Verify that the user can select any option from the dropdown field | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Select any option from the field |  | Any option should be selectable | Any option is selectable | Pass
ALP_BOA_21 | Check whether the dropdown field accept valid option | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Select valid option from the field 4.Click send button | Muvattupuzha | Dropdown field should accept valid option | Dropdown field accepts valid option | Pass
ALP_BOA_22 | Verify that by clicking send button with valid datas appointment will be successful | 1.Open www.alshifapolyclinic.com 2.Click on the book appointment 3.Enter valid datas 4.Click on the send button |  | Proper appointment successful message should be display | Appointment successful message is displayed | Pass
ALP_BOA_23 | Verify that the booking details will send to the phone or email | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Enter valid datas 4.Click on the send button |  | Booking details should send to phone or email | Booking details is not received on the phone or email | Fail

## FEEDBACK
AL-SHIFA POLYCLINIC
Version Number : Verified By :Rugma Raghav Environment Details :Windows 11, Google Chrome(120) |  |  |  | Tested By :Amal Jose Date :01-04-2024 Module Name :Feedback
Test ID | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Status
ALP_FEB_01 | Verify the time is taken to load the page | 1.Open www.alshifapolyclinic.com 2.Click on the home |  | The page should be load with in seconds | The page is load with in seconds | Pass
ALP_FEB_02 | Check whether the logo is clearly visible on the bottom of the page | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Check logo at left bottom corner |  | Logo should be clearly visible | Logo is clearly visible | Pass
ALP_FEB_03 | Check whether all fields and field names are properly align | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Verify the fields and field names |  | All fields and field names should be properly aligned | All fields and field names are properly aligned | Pass
ALP_FEB_04 | Verify that the send button is clickable | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Click on the send button |  | Send button should be clickable | Send button is clickable | Pass
ALP_FEB_05 | Check whether all fields are writable | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Click on each field |  | All fields should be writable | All fields are writable | Pass
ALP_FEB_06 | Verify that the proper error message will display without entering any data in the fields | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Click on the send button without entering any data |  | Proper error message should be display | Error validation is displayed successfully | Pass
ALP_FEB_07 | Check whether the name field does not accept empty string | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Click on the send button without entering any data on the name field |  | Proper error message should be display | Error validation is displayed successfully | Pass
ALP_FEB_08 | Check whether the name field accept characters | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Enter characters on the field 5.Navigate to next field | Amal | Name field should accept characters | Name field accepts characters | Pass
ALP_FEB_09 | Check whether the name field does not accept numbers and special characters | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Enter special characters and numbers on the field 5.Navigate to next field | 986@# | Name field should not accept special characters and numbers | Name field accepts special characters and numbers | Fail
ALP_FEB_10 | Verify that the name field does not accept full name without space | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Enter the full name without space 5.Navigate to next field | AmalJose | Name field should not accept full name without space | Name field accepts full name without space | Fail
ALP_FEB_11 | Check whether the phone number field does not accept empty string | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Click on the send button without entering any data on the phone number field |  | Proper error message should be display | Error validation is displayed successfully | Pass
ALP_FEB_12 | Check whether the phone number field accept numbers | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Enter numbers on the field 5.Navigate to next field | 9048965083 | Phone number field should accept numbers | Phoneb number field accepts numbers | Pass
ALP_FEB_13 | Check whether the phone number field does not accept characters and special characters | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Enter special characters and characters on the field 5.Navigate to next field | khj$# | Phone number field should not accept special characters and characters | Phone number field accepts special characters and characters | Fail
ALP_FEB_14 | Verify that the message field accept empty string | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Click send button without entering any data on the message field |  | Message field should not accept empty string | Message field not accepts empty string | Pass
ALP_FEB_15 | Check whether the message field accept characters, numbers and special characters | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Enter special characters, numbers and characters on the field 4.Navigate to next field | gfhs@1232#$ | Message field should accept special characters, numbers and characters | Message field accepts special characters, numbers and characters | Pass
ALP_FEB_16 | Verify that the message field accept valid data | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Enter valid data 4.Navigate to next field | Your clinic is very good | Date field should accept valid data | Date field accepts valid data | Pass
ALP_FEB_17 | Verify that by clicking send button with valid datas message will be send successfully | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Enter valid datas 4.Click on the send button |  | Message should be send successfully | Message sended successfully | Pass
ALP_FEB_18 | Check whether the phone number icon and link in the bottom of the page is clickable and redirect to next page | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Click on the phone number icon and link |  | Phone number icon and link should be clickable and should be redirect to next page | Phone number icon and link is clickable but cannot redirects to next page | Fail
ALP_FEB_19 | Check whether the email icon and link in the bottom of the page is clickable and redirect to next page | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Click on the email icon and link |  | Email icon and link should be clickable and should be redirect to next page | Email icon and link is not clickable and cannot redirects to next page | Fail
ALP_FEB_20 | Verify that the alignment of the description under 'About' title is correct | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Verify the alignment of the description |  | Alignment should be correct | Alignment is correct | Pass
ALP_FEB_21 | Verify the font size of the description under 'About' title is correct | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Verify the font size of the description |  | Font size of the description should be correct | Font size of the description is correct | Pass
ALP_FEB_22 | Ensure that the social media icons of facebook and instagram on the bottom of the page is clickable and redirect to respective pages | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Click on the facebook and instagram icons |  | Social media icons should be clickable and should be redirect to respective pages | Social media icons is clickable and redirects to respective pages | Pass
ALP_FEB_23 | Verify that the google icon on the bottom of the page is clickable and redirect to next page | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Click on the google icon |  | Google icon should be clickable and should be redirect to next page | Google icon is clickable and redirects to next page | Pass

## BUG REPORT
AL-SHIFA POLYCLINIC
Identified By:Amal Jose Reported To:Rugma Raghav Environment Details:Windows 11,Google Chrome(120) Date:01-04-2024
Bug ID | Expected Result | Bug Summary | Steps To Reproduce | Severity | Priority | Screenshot | Status
ALP_HOM_09 | Alignment should be correct | Alignment is not correct | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Check the alignment of text's under 'Services' title | Minor | Low | https://drive.google.com/file/d/1kiFIF1InS38S2B9T-oET4wE9RmBnQX1o/view?usp=drive_link | New
ALP_HOM_10 | Spelling of the text's should be correct | Spelling of the text is not correct | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Check the spelling mistakes under 'DENTAL IMPLANTS' title | Trivial | Low | https://drive.google.com/file/d/1HR65fACmu52FR6cEkUJqdkoWqtBRCRT4/view?usp=drive_link | New
ALP_HOM_12 | Alignment should be correct | Alignment is not correct | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Check the alignment of text's under 'VISION' title | Minor | Low | https://drive.google.com/file/d/1x09gfVaWNkHhkmNHuZBqDEm_zomAEP2H/view?usp=drive_link | New
ALP_HOM_13 | Alignment should be correct | Alignment is not correct | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Check the alignment of text's under 'MISSION' title | Minor | Low | https://drive.google.com/file/d/11imPzSfJ_1t3_ILia70cpRGc9v61swwB/view?usp=drive_link | New
ALP_HOM_14 | Spelling of the names should be correct | Spelling of the name is not correct | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Check the spelling mistakes in the names of doctors | Trivial | High | https://drive.google.com/file/d/1tc5JzBR3IK8KGG_BQVa5TwMW1Wjye6a8/view?usp=drive_link | New
ALP_HOM_17 | The names should be correct and descriptions should be understandable | Correct names is not there and descriptions is not understandable | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Check the names and descriptions | Minor | High | https://drive.google.com/file/d/170LwJVvji1K4Ld3b0hran9jDGUshxong/view?usp=drive_link | New
ALP_ABO_03 | Alignment should be correct | Alignment is not correct | 1.Open www.alshifapolyclinic.com 2.Click on the about 3.Check the alignment of the text's under 'AL-SHIFA POLY CLINIC' title | Minor | Low | https://drive.google.com/file/d/1Qqu0ELWd7maqZfAl0aBzt0EZDXCK9cIJ/view?usp=drive_link | New
ALP_ABO_04 | Spelling of the names should be correct | Spelling of the name is not correct | 1.Open www.alshifapolyclinic.com 2.Click on the about 3.Check the spelling mistakes in the names of doctors | Trivial | High |  | Old
ALP_ABO_05 | Alignment should be correct | Alignment is not correct | 1.Open www.alshifapolyclinic.com 2.Click on the about 3.Check the alignment of descriptions | Minor | Low | https://drive.google.com/file/d/1JTlTcPs6FyrinGN9c7LsQ62_DEir_OJ4/view?usp=drive_link | New
ALP_ABO_06 | Icons should be clickable and redirect to next pages | Icons are not clickable | 1.Open www.alshifapolyclinic.com 2.Click on the about 3.Click on the linkedin and whatsapp icons | Minor | High | https://drive.google.com/file/d/1gEWr8Qc32bVHgjTWU9ZnUCyga1t-yT3B/view?usp=drive_link | New
ALP_ABO_07 | Alignment should be correct | Alignment is not correct | 1.Open www.alshifapolyclinic.com 2.Click on the about 3.Check the alignment of text's under 'VISION' title | Minor | Low |  | Old
ALP_ABO_08 | Alignment should be correct | Alignment is not correct | 1.Open www.alshifapolyclinic.com 2.Click on the about 3.Check the alignment of text's under 'MISSION' title | Minor | Low |  | Old
ALP_HMP_05 | Alignment should be correct | Alignment is not correct | 1.Open www.alshifapolyclinic.com 2.Click on the homeopathy 3.Check the alignment of the text's in the page | Minor | Low | https://drive.google.com/file/d/1u3d7xdBkf09-20E0csqABTTN61unDq0K/view?usp=drive_link | New
ALP_DEN_04 | There should not be any spelling mistakes in the descriptions | Spelling mistake is there in the descriptions | 1.Open www.alshifapolyclinic.com 2.Click on the dentistry 3.Check the spelling mistakes in the descriptions | Trivial | Low |  | Old
ALP_CON_02 | Alignment should be correct | Alignment is not correct | 1.Open www.alshifapolyclinic.com 2.Click on the contact 3.Check the alignment of the text's in the page | Minor | Low | https://drive.google.com/file/d/1EuIsio2obcq5mSrFKQQq728iMUHIHWsr/view?usp=drive_link | New
ALP_CON_03 | All titles of the page should be able to see after few seconds of loading | User cannot see'Working Hours' title after loading few seconds | 1.Open www.alshifapolyclinic.com 2.Click on the contact 3.Check the titles of the page after few seconds of loading | Minor | High | https://drive.google.com/file/d/1lTrxEiOqigiQn5i68740VIJb5-yKO2c8/view?usp=drive_link | New
ALP_CON_06 | Phone number icon and link should be clickable and should be redirect to next page | Phone number icon and link is clickable but cannot redirects to next page | 1.Open www.alshifapolyclinic.com 2.Click on the contact 3.Click on the phone number icon and link | Major | High | https://drive.google.com/file/d/16oYiVeV-lufnbk1l_LWk5J9yPNNjyt-n/view?usp=drive_link | New
ALP_CON_07 | Email icon and link should be clickable and should be redirect to next page | Email icon and link is not clickable and cannot redirects to next page | 1.Open www.alshifapolyclinic.com 2.Click on the contact 3.Click on the email icon and link | Major | High | https://drive.google.com/file/d/1S4s7oN_cjmfxKNw5GbB61kbFms2JKsnR/view?usp=drive_link | New
ALP_BOA_02 | Logo should be clearly visible | Logo is not clearly visible | 1.Open www.alshifapolyclinic.com 2.Click on the book appointment 3.Check logo at left top corner | Minor | High | https://drive.google.com/file/d/1fxSxpx-Fh4G-gL5ulR6EpqmGtwg1va7r/view?usp=drive_link | New
ALP_BOA_04 | Should contain asterick symbol | Asterick symbol is not present | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Verify the fields | Minor | High | https://drive.google.com/file/d/12XM4N92cmvBXjHprAQ9Rcw2BAahcPY_K/view?usp=drive_link | New
ALP_BOA_11 | Name field should not accept special characters and numbers | Name field accepts special characters and numbers | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Enter special characters and numbers on the field 4.Navigate to next field | Major | Low | https://drive.google.com/file/d/1HT5VZO9LLA-WvOkZtKICE0Ijn32cleE2/view?usp=drive_link | new
ALP_BOA_12 | Name field should not accept full name without space | Name field accepts full name without space | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Enter the full name without space 4.Navigate to next field | Minor | Low | https://drive.google.com/file/d/1nVqmdJmM3mA-T7Ik3rvqj4nRWApigYfs/view?usp=drive_link | new
ALP_BOA_15 | Contact number field should not accept special characters and characters | Contact number field accepts special characters and characters | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Enter special characters and characters on the field 4.Navigate to next field | Major | Low | https://drive.google.com/file/d/16wRZ82uPOgc2SfkHs6IlLHZRiBKPGAtf/view?usp=drive_link | New
ALP_BOA_23 | Booking details should send to phone or email | Booking details is not received on the phone or email | 1.Open www.alshifapolyclinic.com 2.Click on the book appoinment 3.Enter valid datas 4.Click on the send button | Minor | High |  | New
ALP_FEB_09 | Name field should not accept special characters and numbers | Name field accepts special characters and numbers | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Enter special characters and numbers on the field 5.Navigate to next field | Major | Low | https://drive.google.com/file/d/1n8IdTd0C1WgRHBCPbW0luVskSozTuc5c/view?usp=drive_link | new
ALP_FEB_10 | Name field should not accept full name without space | Name field accepts full name without space | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Enter the full name without space 5.Navigate to next field | Minor | Low |  | New
ALP_FEB_13 | Phone number field should not accept special characters and characters | Phone number field accepts special characters and characters | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Enter special characters and characters on the field 5.Navigate to next field | Major | Low | https://drive.google.com/file/d/19Afd3OAKxztmM3492VpSVAGIr5TdhNC3/view?usp=drive_link | New
ALP_FEB_18 | Phone number icon and link should be clickable and should be redirect to next page | Phone number icon and link is clickable but cannot redirects to next page | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Click on the phone number icon and link | Major | High |  | New
ALP_FEB_19 | Email icon and link should be clickable and should be redirect to next page | Email icon and link is not clickable and cannot redirects to next page | 1.Open www.alshifapolyclinic.com 2.Click on the home 3.Scroll down to feedback page 4.Click on the email icon and link | Major | High |  | New

## DEFECT DISTRIBUTION
AL-SHIFA POLYCLINIC
Module Name | Defect Distribution
Home | 6
About | 6
Homeopathy | 1
Dentistry | 1
Contact | 4
Book Appointment | 6
Feedback | 5

## TEST REPORT
AL-SHIFA POLYCLINIC
Module Name | Test Case Passed | Test Case Failed | Total Test Cases
Home | 14 | 6 | 20
About | 5 | 6 | 23
Homeopathy | 6 | 1 | 7
Dentistry | 4 | 1 | 5
Contact | 4 | 4 | 8
Book Appointment | 17 | 6 | 23
Feedback | 18 | 5 | 23
S